## Dashboard
Construction Job Costing Dashboard
Project Name
Project Reference
Forecast exception means forecast at completion exceeds budget by more than the editable threshold on Setup.
| Current Budget (USD) |  |  | Forecast at Completion (USD)
| Committed Cost (USD) |  |  | Budget Variance (Budget Less Forecast) (USD)
| Actual Cost (USD) |  |  | Forecast Exceptions
| Cost to Complete (USD) |  |  | Open Commitments (USD)
| Commitment Status Summary | Amount (USD)
Open Commitments (USD)
Closed Commitments (USD)
Cancelled Commitments (USD)
| Cost Code | Cost Code Description | Budget (USD) | Committed Cost (USD) | Actual Cost (USD) | Forecast Adjustment (USD) | Forecast Base (USD) | Cost to Complete (USD) | Forecast at Completion (USD) | Budget Variance (USD) | Forecast Exception
Commitments Missing Budget Code
Actuals Missing Budget Code

## Setup
Project Setup and Operational Controls
Project Identification
Project Name | Cedar Grove Office Renovation | Commitment Status List
Project Reference | CG-2601 | Open
Forecast Exception Threshold (USD) | 0 | Closed
Cancelled
The forecast exception threshold is a user-defined management setting only. It has no legal, accounting, audit, or regulatory meaning.

## Budget
Budget Ledger
Project
Enter one unique budget cost code per populated row. Budget rows drive the Job Cost Report.
Cost Code | Cost Code Description | Budget Amount (USD) | Forecast Adjustment (USD) | Notes
03-100 | Sitework | 40000 | 0 | Initial sitework allowance
03-200 | Concrete | 85000 | 5000 | Remaining concrete exposure
03-300 | Framing | 120000 | -3000 | Updated framing outlook
04-100 | Masonry | 60000 | 2500 | Exterior masonry allowance
05-100 | Structural Steel | 95000 | 0 | Structural steel package
06-100 | Roofing | 55000 | 1500 | Roofing contingency
07-100 | Doors and Windows | 70000 | 0 | Openings package allowance
09-100 | Finishes | 110000 | 4000 | Finishes escalation allowance

## Commitments
Commitments Ledger
Project
Open and Closed commitments are included in committed cost. Cancelled commitments remain visible but are excluded.
Commitment ID | Cost Code | Vendor | Commitment Amount (USD) | Status | Reference / Notes | Cost Code Check
COM-100 | 03-100 | ClearPath Site Services | 24500 | Open | Site clearing purchase order
COM-200 | 03-200 | Rockford Concrete LLC | 80000 | Open | Concrete subcontract
COM-300 | 03-300 | Timberline Framing Inc. | 115000 | Open | Framing subcontract
COM-400 | 04-100 | Northline Masonry LLC | 54000 | Open | Masonry subcontract
COM-500 | 05-100 | Iron Ridge Steel LLC | 92000 | Open | Structural steel fabrication
COM-600 | 06-100 | WeatherShield Roofing | 51000 | Open | Roofing subcontract
COM-700 | 07-100 | Metro Openings Supply | 66500 | Closed | Doors and windows package
COM-900 | 09-100 | Precision Interior Group | 104000 | Open | Interior finishes subcontract

## Actuals
Actual Cost Ledger
Project
Enter invoice-based actual cost transactions. Commitment ID is a reference field only and does not calculate billing balances.
Invoice Date | Invoice / Reference | Cost Code | Commitment ID | Vendor | Actual Amount (USD) | Notes | Cost Code Check
2026-04-05 | INV-1045 | 03-100 | COM-100 | ClearPath Site Services | 14250 | Mobilization and clearing
2026-04-12 | INV-2240 | 03-200 | COM-200 | Rockford Concrete LLC | 27000 | Footing progress billing
2026-04-18 | INV-3177 | 03-300 | COM-300 | Timberline Framing Inc. | 37000 | Framing progress billing
2026-04-22 | INV-4110 | 04-100 | COM-400 | Northline Masonry LLC | 16500 | Masonry mobilization
2026-04-25 | INV-5294 | 05-100 | COM-500 | Iron Ridge Steel LLC | 23000 | Steel deposit billing
2026-04-27 | INV-6018 | 06-100 | COM-600 | WeatherShield Roofing | 11000 | Roofing materials delivery
2026-04-29 | INV-7142 | 07-100 | COM-700 | Metro Openings Supply | 32500 | Window package billing
2026-05-02 | INV-9031 | 09-100 | COM-900 | Precision Interior Group | 18000 | Interior finishes mobilization

## Job Cost Report
Job Cost Report
Project
This report is calculated from the Budget, Commitments, Actuals, and Setup sheets. It does not replace accounting software.
Cost Code | Cost Code Description | Budget (USD) | Committed Cost (USD) | Actual Cost (USD) | Forecast Adjustment (USD) | Forecast Base (USD) | Cost to Complete (USD) | Forecast at Completion (USD) | Budget Variance (Budget Less Forecast) (USD) | Forecast Exception

## Instructions
Instructions
Getting Started
1 | Enter the project name, reference, and forecast exception threshold on Setup.
2 | Add one unique cost code and budget amount per Budget row.
3 | Enter the current Forecast Adjustment for each cost code when remaining-cost expectations change.
4 | Enter vendor commitments on Commitments and select the matching Budget cost code.
5 | Enter invoice-based actual costs on Actuals using m/d/yyyy invoice dates.
6 | Review the Dashboard and Job Cost Report for budget variance and forecast exceptions.
How Forecast Works
The report compares each cost code’s Budget, Committed Cost, Actual Cost, and Forecast Adjustment.
Cost to Complete cannot be less than USD 0.00.
Forecast Adjustment changes the remaining-cost forecast; it does not revise the budget.
Cancelled commitments remain in the Commitments ledger but are excluded from Committed Cost.
Data Entry Checks
Cost codes in Commitments and Actuals should match a Budget cost code.
Review Missing Budget Code warnings before relying on Dashboard totals.
The workbook contains 150 prepared rows on each operational sheet. Extend formulas, data validation, report rows, and chart ranges if more capacity is needed.
Workbook Limits
This workbook tracks one project only.
It does not calculate WIP, earned revenue, invoicing, payments, tax treatment, financial statements, or certified profitability.
It does not reconcile invoices to commitments or determine whether a commitment is fully billed.
It does not perform quantity takeoff, assembly estimating, or US customary unit conversion.
The results depend on user-entered budget, commitment, actual-cost, and forecast-adjustment data.