## Dashboard
Construction Material Register
Project Name
Selected Material Record ID | MAT-001 | Selected Record Status
Item |  | Issued Quantity
Description |  | Adjustment Quantity
Unit |  | On-Hand Quantity
Location |  | Planned Balance
Planned Quantity |  | Quantity Variance
Received Quantity |  | Shortage Flag
Register Counts
Active Item-Location Records
Records With Shortages
Movement Entries Recorded
Quantities are shown for the selected material item-location record. This workbook does not convert units or confirm physical stock. Reconciliation depends on complete user-entered movements.

## Setup
Project Setup and Validation Lists
Project Name | Riverside Commons Building A
Project Number | RC-2026-014
Report Date | 2026-09-04
Prepared By | Alex Morgan
Unit Labels |  | Locations | Movement Types
Unit Label |  | Location | Movement Type
EA |  | Foundation Zone A | Received
ft |  | North Laydown | Issued
sq ft |  | Utility Trench | Adjustment
cu yd |  | Roof Level | Received
lb |  | East Storage | Issued
gal |  | Level 2 | Adjustment
ton |  | South Laydown | Received
bag |  | Mechanical Room | Issued
Adjustment
List Maintenance Note
Users may add, revise, or remove unit labels, locations, and movement types for this project. The workbook does not create unit conversions.

## Materials
Materials Register
Project Name
Material Record ID | Item | Description | Unit | Location | Planned Quantity | Received Quantity | Issued Quantity | Adjustment Quantity | On-Hand Quantity | Planned Balance | Quantity Variance | Shortage Flag | Reference Unit Cost (USD) | Planned Reference Value (USD) | Notes
MAT-001 | CONC-4000 | Ready-mix concrete, 4,000 psi | cu yd | Foundation Zone A | 80
MAT-002 | REBAR-NO4 | No. 4 reinforcing bar, 20 ft length | EA | Foundation Zone A | 180
MAT-003 | FORMPLY-34 | Form plywood, 3/4 in, 4 ft x 8 ft sheet | EA | North Laydown | 120
MAT-004 | LBR-2X4-8 | Lumber, 2 in x 4 in x 8 ft | EA | North Laydown | 240
MAT-005 | AB-34X12 | Anchor bolt, 3/4 in x 12 in | EA | Foundation Zone A | 48
MAT-006 | PVC-4 | PVC pipe, 4 in diameter | ft | Utility Trench | 400
MAT-007 | STONE-57 | #57 crushed stone | cu yd | Utility Trench | 120
MAT-008 | MEMBRANE | Roofing membrane | sq ft | Roof Level | 5000
MAT-009 | SEALANT | Construction joint sealant | gal | East Storage | 30
MAT-010 | GYP-58 | Gypsum board, 5/8 in, 4 ft x 8 ft sheet | EA | Level 2 | 300

## Movements
Material Movements Ledger
Project Name
Movement ID | Movement Date | Material Record ID | Item | Unit | Location | Movement Type | Quantity | Delivery/Issue Reference | Entered By | Notes
MOV-001 | 2026-08-25 | MAT-001 |  |  |  | Received | 60 | DEL-1001 | Alex M. | Sample delivery
MOV-002 | 2026-08-27 | MAT-001 |  |  |  | Issued | 25 | ISS-2001 | Alex M. | Sample placement issue
MOV-003 | 2026-08-26 | MAT-002 |  |  |  | Received | 180 | DEL-1002 | Alex M. | Sample delivery
MOV-004 | 2026-08-26 | MAT-003 |  |  |  | Received | 100 | DEL-1003 | Alex M. | Sample delivery
MOV-005 | 2026-08-28 | MAT-003 |  |  |  | Issued | 40 | ISS-2002 | Alex M. | Sample formwork issue
MOV-006 | 2026-08-27 | MAT-004 |  |  |  | Received | 240 | DEL-1004 | Alex M. | Sample delivery
MOV-007 | 2026-08-29 | MAT-004 |  |  |  | Issued | 70 | ISS-2003 | Alex M. | Sample framing issue
MOV-008 | 2026-08-29 | MAT-004 |  |  |  | Adjustment | -5 | ADJ-3001 | Alex M. | Sample damaged material adjustment
MOV-009 | 2026-08-28 | MAT-006 |  |  |  | Received | 250 | DEL-1005 | Alex M. | Sample delivery
MOV-010 | 2026-08-28 | MAT-007 |  |  |  | Received | 150 | DEL-1006 | Alex M. | Sample delivery

## Reconciliation
Material Reconciliation | [12 empty] | Shortage List
Project Name
[13 empty] | Material Record ID | Item | Description | Unit | Location | On-Hand Quantity | Planned Balance | Quantity Variance
Material Record ID | Item | Description | Unit | Location | Planned Quantity | Received Quantity | Issued Quantity | Adjustment Quantity | On-Hand Quantity | Planned Balance | Quantity Variance | Shortage Flag
Location View
Selected Location | Foundation Zone A
Material Record ID | Item | Description | Unit | Location | Planned Quantity | Received Quantity | Issued Quantity | Adjustment Quantity | On-Hand Quantity | Planned Balance | Quantity Variance | Shortage Flag

## Instructions
Construction Material Register Instructions
Workbook Use
1 | 1. Complete project information on the Setup sheet.
2 | 2. Review or update the Unit Labels and Locations lists on Setup.
3 | 3. Add one material item-location record on the Materials sheet for each project material and location combination.
4 | 4. Enter planned quantities on the Materials sheet.
5 | 5. Record all delivery receipts, material issues, and adjustments on the Movements sheet.
6 | 6. Review calculated on-hand quantity, planned balance, quantity variance, and shortage flag on Materials.
7 | 7. Use Reconciliation to review the full register, the shortage list, and the selected location view.
8 | 8. Use Dashboard to review one selected material item-location record.
User Inputs
Input | Where Entered
Project name, project number, report date, prepared by | Setup
Unit labels and locations | Setup
Material record ID, item, description, unit, location, planned quantity | Materials
Optional reference unit cost in USD | Materials
Receipt, issue, and adjustment movements | Movements
Movement date, quantity, reference, entered by, and notes | Movements
Calculation Definitions
Calculation | Definition
Received Quantity | Total of all Received movement quantities for the Material Record ID.
Issued Quantity | Total of all Issued movement quantities for the Material Record ID.
Adjustment Quantity | Total of all signed Adjustment movement quantities for the Material Record ID.
On-Hand Quantity | Received Quantity minus Issued Quantity plus Adjustment Quantity.
Planned Balance | Planned Quantity minus Issued Quantity.
Quantity Variance | On-Hand Quantity minus Planned Balance.
Shortage Flag | SHORTAGE when Quantity Variance is less than zero; otherwise OK.
Adjustment Entry Guidance
• | Enter a positive Adjustment quantity to increase the recorded on-hand quantity.
• | Enter a negative Adjustment quantity to reduce the recorded on-hand quantity.
• | Include a reason in the Notes column for every adjustment.
• | Use the material record’s stated unit. Do not convert quantities in the workbook.
Important Limits
Note | This workbook is a project material register and reconciliation tool. It does not estimate takeoff quantities, create purchase orders, certify inventory, replace warehouse controls, track reusable stock transfers, or calculate reorder points. Quantity results depend on complete and accurate user-entered movements and do not prove physical stock.
Sample Data Note
Sample Data | The workbook includes sample material records and sample movements for demonstration. Replace or delete sample entries before using the workbook for a live project.