## Dashboard
Construction Schedule Dashboard
Project Name | [6 empty] | As-of Date
Active Tasks |  |  | Completed Tasks |  |  | Late Tasks |  | Update Needed
Overall Progress
Phase Summary
Phase | Task Count | Phase Progress | Late Tasks
Late Tasks Beyond Internal Threshold
Task ID | Phase | Task | Owner | Planned Finish | Current Finish | Days Variance (Calendar Days) | Status

## Setup
Construction Schedule Setup
Project Setup
Project Name | Sample Community Retail Build-Out
Project Reference | Sample Planning Schedule
Timeline Start | 2026-04-01
As-of Date | 2026-05-01
Late Threshold (Calendar Days) | 0
Editable Lists
Phase List | Phase | Owner List | Owner
1 | Preconstruction | 1 | Project Manager
2 | Sitework | 2 | Superintendent
3 | Foundations | 3 | Concrete Foreman
4 | Structure | 4 | Steel Foreman
5 | Enclosure | 5 | Framing Foreman
6 | MEP | 6 | MEP Foreman
7 | Closeout | 7 | Project Controls
8 |  | 8
9 |  | 9
10 |  | 10
Update project details, phase names, responsible owners, the as-of date, and the internal late threshold before using the schedule. The workbook supports up to 10 phase-list entries and 10 owner-list entries without structural changes.

## Master Schedule
Construction Master Schedule
Yellow cells are task inputs. Gray cells are calculated. Dependencies are informational only and do not recalculate dates.
Weekly Timeline
Task ID | Phase | Task | Owner | Planned Start | Planned Finish | Dependency | Percent Complete | Current Finish | Duration (Calendar Days) | Days Variance (Calendar Days) | Status | Late List Rank
C-001 | Preconstruction | Notice to Proceed | Project Manager | 2026-04-01 | 2026-04-03 |  | 100% | 2026-04-03
C-002 | Preconstruction | Site Logistics Plan | Superintendent | 2026-04-04 | 2026-04-08 | C-001 | 100% | 2026-04-08
C-003 | Sitework | Mobilization | Superintendent | 2026-04-09 | 2026-04-15 | C-002 | 100% | 2026-04-16
C-004 | Foundations | Footing Excavation | Superintendent | 2026-04-16 | 2026-04-22 | C-003 | 75% | 2026-04-23
C-005 | Foundations | Place Footings | Concrete Foreman | 2026-04-23 | 2026-04-29 | C-004 | 25% | 2026-04-30
C-006 | Structure | Structural Steel Erection | Steel Foreman | 2026-04-30 | 2026-05-15 | C-005 | 0% | 2026-05-18
C-007 | Enclosure | Exterior Framing | Framing Foreman | 2026-05-18 | 2026-05-29 | C-006 | 0% | 2026-05-29
C-008 | MEP | Underground Plumbing | MEP Foreman | 2026-04-23 | 2026-05-01 | C-004 | 50% | 2026-05-02
C-009 | Closeout | Owner Training | Project Manager | 2026-06-15 | 2026-06-16 | C-007 | 0%

## Milestones
Construction Schedule Milestones
Optional high-level milestone register. Entries do not feed task dependencies, task dates, phase progress, or Dashboard calculations.
Milestone ID | Milestone | Linked Task ID | Owner | Baseline Date | Current Date | Days Variance (Calendar Days) | Timing Flag | Notes
M-001 | Notice to Proceed Complete | C-001 | Project Manager | 2026-04-03 | 2026-04-03 |  |  | Project authorization received.
M-002 | Site Logistics Plan Complete | C-002 | Superintendent | 2026-04-08 | 2026-04-08 |  |  | Site access and logistics plan issued.
M-003 | Mobilization Complete | C-003 | Superintendent | 2026-04-15 | 2026-04-16 |  |  | Mobilization completed one day late.
M-004 | Footing Excavation Complete | C-004 | Superintendent | 2026-04-22 | 2026-04-23 |  |  | Excavation turnover documented.
M-005 | Footings Complete | C-005 | Concrete Foreman | 2026-04-29 | 2026-04-30 |  |  | Concrete footing placement complete.
M-006 | Steel Erection Complete | C-006 | Steel Foreman | 2026-05-15 | 2026-05-18 |  |  | Structural steel completion tracking.
M-007 | Exterior Framing Complete | C-007 | Framing Foreman | 2026-05-29 | 2026-05-29 |  |  | Exterior framing completion target.
M-008 | Underground Plumbing Complete | C-008 | MEP Foreman | 2026-05-01 | 2026-05-02 |  |  | Underground plumbing completion recorded.
M-009 | Owner Training Complete | C-009 | Project Manager | 2026-06-16 |  |  |  | Upcoming owner training milestone.

## Instructions
Construction Schedule Workbook Instructions
Workbook Use
1. | Update Project Name, Timeline Start, As-of Date, phase names, owners, and the internal late threshold on the Setup sheet.
2. | Enter one row per task on Master Schedule.
3. | Use a unique Task ID for every task.
4. | Enter Planned Start and Planned Finish as the baseline task dates.
5. | Use the Dependency field only for a simple predecessor Task ID reference.
6. | Update Percent Complete and Current Finish as the task progresses.
7. | Review phase progress, late tasks, and summary indicators on Dashboard.
8. | Use the optional Milestones sheet to track high-level dates without changing the master task schedule.
Calculation Definitions
Field | Definition
Duration (Calendar Days) | Planned Finish minus Planned Start, plus one Calendar Day.
Days Variance (Calendar Days) | Current Finish minus Planned Finish.
Phase Progress | Planned-duration-weighted Percent Complete for tasks in the same phase.
Late Threshold | Editable internal Calendar Day threshold used for late-task flags and Dashboard reporting.
Update Needed | A task needs a Current Finish update based on the as-of date or completion status.
Functional Boundaries
Important | This workbook is a practical construction planning schedule for one project. It does not perform CPM calculations, resource leveling, critical-path analysis, delay analysis, contractual schedule updates, or delay-entitlement evaluation. Dependencies are informational and do not automatically move dates.
Input Legend
Light yellow cells | User inputs.
Light gray cells | Calculated values.
Red highlights | Late timing or positive late variance.
Green highlights | Completed tasks or early timing variance.
Yellow highlights | Update needed or planned-finish marker.