## Dashboard
Construction WIP Dashboard
Internal active-job work-in-progress summary
Reporting Period End (MM/DD/YYYY)
Billing Variance Alert Threshold
Active Jobs | Revised Contract Value (USD) | Revised Estimated Cost (USD) | Cost to Date (USD)
Cost-to-Cost Earned Amount (USD) | Billings to Date (USD) | Under/(Over) Billing (USD) | Projected Gross Profit (USD)
Optional Review Tools
Quick Project Lookup (optional) | Selected Project Name | Current Job Status | Average Cost-to-Cost %

## Company WIP
Company Work-in-Progress Schedule
Linked project-level schedule for internal review
Reporting Period End
Project ID | Project Name | Customer | Project Manager | Job Status | Revised Contract Value (USD) | Revised Estimated Cost (USD) | Cost to Date (USD) | Cost-to-Cost % | Cost-to-Cost Earned Amount (USD) | Billings to Date (USD) | Under/(Over) Billing (USD) | Projected Gross Profit (USD) | Projected GP % | Billing Variance % | Operational Alert | Data Check
Active-job total

## Project Detail
Project Detail and WIP Calculations
Enter one current-period project record per row. Pale yellow cells are user inputs; gray cells are calculated outputs.
Project ID | Project Name | Customer | Project Manager | Job Status | Original Contract Value (USD) | Approved Change Orders (USD) | Revised Contract Value (USD) | Revised Estimated Cost (USD) | Cost to Date (USD) | Cost-to-Cost % | Cost-to-Cost Earned Amount (USD) | Billings to Date (USD) | Under/(Over) Billing (USD) | Projected Gross Profit (USD) | Projected GP % | Billing Variance % | Operational Alert | Notes | Data Check
AB-2601 | Midtown Office Renovation | Parkline Properties LLC | Jordan Lee | Active | 1250000 | 75000 |  | 1040000 | 624000 |  |  | 700000 | [5 empty] | Phased interior work
AB-2602 | Westgate Warehouse Expansion | Summit Distribution LLC | Morgan Diaz | Active | 860000 | 40000 |  | 760000 | 380000 |  |  | 420000 | [5 empty] | Steel package in progress
AB-2603 | Cedar Ridge Senior Living Refresh | Cedar Ridge Management LLC | Taylor Brooks | Active | 2400000 | 180000 |  | 2180000 | 1744000 |  |  | 2150000 | [5 empty] | Finish work and turnover areas
AB-2604 | Lakeside Retail Shell | Lakeside Retail Group LLC | Casey Nguyen | Active | 510000 | 0 |  | 445000 | 400500 |  |  | 420000 | [5 empty] | Exterior closeout underway
AB-2605 | Northline Manufacturing Addition | Northline Fabrication LLC | Avery Patel | Active | 1750000 | 120000 |  | 1560000 | 624000 |  |  | 650000 | [5 empty] | Foundation and structural work
AB-2606 | Pine Street Clinic Remodel | Pine Street Medical Group LLC | Cameron Reed | Active | 685000 | 15000 |  | 590000 | 442500 |  |  | 500000 | [5 empty] | MEP rough-in complete
AB-2607 | Harborview Tenant Improvement | Harborview Holdings LLC | Riley Morgan | Active | 1100000 | 55000 |  | 980000 | 735000 |  |  | 760000 | [5 empty] | Millwork and finishes in progress
AB-2608 | Granite Peak Service Center | Granite Peak Services LLC | Devon Clark | Active | 940000 | 0 |  | 805000 | 281750 |  |  | 365000 | [5 empty] | Site and slab activities
AB-2609 | Elmwood Community Center Upgrade | Elmwood Facilities LLC | Quinn Foster | Active | 1380000 | 92000 |  | 1240000 | 806000 |  |  | 900000 | [5 empty] | Interior renovation and equipment installation

## Instructions
Instructions and Workbook Limits
Use this internal project-controls workbook for prepared monthly WIP review.
Monthly Workflow
• | 1. On Dashboard, enter the Reporting Period End using MM/DD/YYYY.
• | 2. Optionally enter a Billing Variance Alert Threshold on Dashboard. Leave it blank if no operational review flag is wanted.
• | 3. On Project Detail, maintain one current-period project row for each job. Enter user-input values only in the pale yellow cells.
• | 4. Confirm each Job Status. Dashboard and the Company WIP total row include only rows marked Active.
• | 5. Review calculated outputs, Data Check messages, and Operational Alert messages.
• | 6. Use Company WIP for the linked company schedule. Do not enter or overwrite values there.
User-Entered Fields
• | Original Contract Value (USD): Current original contract value for the job.
• | Approved Change Orders (USD): Approved additions or deductions to the original contract value.
• | Revised Estimated Cost (USD): Current project-level estimated cost used for the internal comparison.
• | Cost to Date (USD): Current cumulative project cost entered by the user.
• | Billings to Date (USD): Current cumulative project billings entered by the user.
• | Job Status: Use Active, Hold, or Closed. Active is the status included in Dashboard and Company WIP totals.
• | Notes: Optional operational context for the project record.
Calculated Outputs
• | Revised Contract Value (USD) equals Original Contract Value plus Approved Change Orders.
• | Cost-to-Cost % equals Cost to Date divided by Revised Estimated Cost.
• | Cost-to-Cost Earned Amount (USD) equals Revised Contract Value multiplied by Cost-to-Cost %.
• | Under/(Over) Billing (USD) equals Cost-to-Cost Earned Amount less Billings to Date. Positive values indicate an underbilled position in this workbook display; negative values indicate an overbilled position.
• | Projected Gross Profit (USD) equals Revised Contract Value less Revised Estimated Cost.
• | Billing Variance % equals Under/(Over) Billing divided by Revised Contract Value.
• | Operational Alert shows Review only when an optional Dashboard threshold is entered and the Billing Variance % meets or exceeds that user-defined threshold in either direction.
• | Data Check identifies incomplete core amount inputs and Cost to Date values that exceed Revised Estimated Cost.
Functional Limits
• | This workbook is an internal project-controls aid, not a transaction-level job-costing system.
• | The cost-to-cost earned amount is an operational calculation for comparison purposes. It does not establish a revenue-recognition policy or determine financial reporting treatment.
• | The workbook does not create pay applications, tax reports, audited financial statements, or historical accounting evidence.
• | The workbook does not verify contracts, change orders, source job costs, billings, or customer balances.
• | The prepared capacity is 100 project rows. Extending beyond row 111 requires extending the Project Detail formulas, Company WIP links, table ranges, conditional formatting, Dashboard formulas, and chart ranges.
• | Formula results are calculated by Excel when the workbook is opened or recalculated. An openpyxl generator writes formulas but does not independently produce Excel-calculated cached results.